## Sheet1
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7
Iteration 2 — Expanded Risk Assessment (Week 5)
(Added risks based on stakeholder interviews)
Risk ID | Description | Category | Likelihood | Impact | Score | Rating
R01 | No MFA enforced on Azure AD accounts | Cloud / Identity | 4 | 5 | 20 | Critical
R02 | Azure Blob Storage publicly accessible | Cloud / Data | 4 | 5 | 20 | Critical
R03 | Permissive NSG rules (RDP open to internet) | Cloud / Network | 4 | 4 | 16 | High
R04 | Flat network (no VLAN segmentation) | Network | 4 | 4 | 16 | High
R05 | No TLS encryption for internal services | Network / Data | 3 | 4 | 12 | Medium
R06 | Unpatched workstations | Endpoint | 3 | 4 | 12 | Medium
R07 | No formal offboarding / inactive accounts | Identity | 3 | 4 | 12 | Medium
R08 | No incident response plan | Governance | 4 | 4 | 16 | High
R09 | VPN not reviewed, possible weak configuration | Network | 3 | 4 | 12 | Medium
R10 | No cybersecurity awareness training | People | 3 | 3 | 9 | Medium
R11 | Unmanaged network switches | Network | 4 | 3 | 12 | Medium
R12 | Backups not tested | Data / Continuity | 3 | 4 | 12 | Medium